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Oswegatchie Fire Station Building Committee Meeting

July 3, 2025
*AMENDED*

Meeting called to order at 6:30pm

Pledge of Allegiance

Members Present:  Robert Tuneski, Rocco Bracciale, Wayne Gilpin, Ted Olynciw, Richard Muckle, Paul Rafuse, Jennifer Bracciale Matthew Blankenship
Members Absent:  None
Guests:   Fire Services Director Chris Haley, Steve Smith, Eric Cantar, Bob Banning, Treasurer Abbas Danesh, Purchasing Agent Shea Davy
Public Comment:  None

Opening Remarks:  
B. Tuneski stated he received the construction estimate and renovate as new estimate from Downes.
Approval of Minutes:


MOTION by M. Blankenship, second J. Bracciale to approve the June 5, 2025 minutes


FOR:
  B. Tuneski, R. Bracciale, W. Gilpin, T. Olynciw, R. Muckle, P. Rafuse, J. Bracciale

ABSTAIN:  M. Blankenship

Approval of Invoices:

MOTION by T. Olynciw, second. Gilpin to pay Downes invoice #5 in the amount of $6,320.00.

FOR:  Unanimous

MOTION by T. Olynciw, second by W. Gilpin to pay SPA invoice #25-2113 in the amount of $17,300.00.
FOR:
 Unanimous

Old Business:

a. The traffic signal will be reassessed after the trees have been cut back.

b. S. Smith handed out a new control budget (Attachment 1) Estimators and designers met and the numbers are in line with each other.
c. Storm water permit was filed a month ago.  There is a 60 day waiting period prior to work beginning.

d. Pre-demolition survey – T. Olynciw indicated the findings were very positive, i.e., no asbestos except for 2,600 square feet of flooring.

e. S. Sinagra does not see any issue with the station alerting system being through fiber-optics

f. E. Cantar will check with SPA’s civil engineer what the lead time is for the DOT permit.
g. S. Smith provided the Construction Document cost estimate. (Attachment 2)
T. Olynciw responded to the letter regarding the number of vacant bays through the town. (Attachment 3)
Current Business:

a. Design status – SPA is waiting for verifications on the traffic signal and from IT.  E. Cantar feels the Downes estimates are in line with SPA projections.  Director Haley will contact IT Director J. Robillard regarding updating the alerting system.
b. Construction estimate is complete and was provided to committee members by S. Smith.
New Business:

a. The Board of Finance will be in attendance at the Board of Selectman’s meeting on 7/22/25 for the Oswegatchie Fire Station presentation.

b. B. Tuneski believes the RTM will be holding an informational session in mid-July or after for the Oswegatchie Fire Station project and also the Ad Hoc report.  The next RTM meeting is scheduled for 8/4/25.

The next Oswegatchie Fire Station Committee meeting is scheduled for 7/17/25 at 6:30pm.

MOTION by M. Blankenship, second J. Bracciale to adjourn.


FOR:  Unanimous
Meeting adjourned 7:15pm
Respectfully submitted by:

Linda Finnegan, Recording Secretary
*Old Business, letter d. amended: no asbestos except for 2600 sq. ft. of flooring
